## Sheet1
Project Risk Management Examples
This tool provides a brief guideline on how to evaluate Probability and Severity for the risks identified in the Project Charter and/or Plan. It also lists common project risks grouped by the different sections in the Project Plan which could be applicable to your project.
Probability Assessment: High - quite probable Medium - more likely than not Low - possible but not likely |  | Severity Assessment: Assess High, Med, Low based on the seriousness of consequences; amount of flexibility in dealing with problems; costs to resolve; resource impacts; scheduling impacts
Project Plan Sections | Risk Categories | Project Risk Examples
Integration Management
Scope Management | Business Requirements | Very vague or very complex
| Scope Definition | - Scope is likely to change - Size of the project ( of deliverables)
Time Management | Changing Priorities | Project priorities likely to change - possible impact on project schedule
| Project Work | Inaccurate or under-estimated project work required for deliverables
| Schedule | Overly-optimistic deadlines
Cost Management | Project Funding | - Cost estimates not accurate - Cost overruns - Funding Cuts
Quality Management | Customizations | Many customizations required
| Data Migration | Current data is poor and difficult to convert to new system
| Documentation & training | Lack of or poor supporting documentation & training
| Quality | Quality standards unmet
| Testing | Testing is not thorough
Resource Management | Lack of Resources | Not enough resources assigned to the project
| Organization | Concerns and/or resistance to process changes
| Project team availability, staff turnover | - Resources not available when needed - Change of resources - Loss of project sponsor during project - Labour strikes or work stoppages
| Skills | Lacking required skill set
| Technology | - Problems with technology impacting other deliverables - Software/hardware dependencies not anticipated - Changes in related systems, programs, etc. - Complex technology - New or unproven technology - Unavailability of technology - Poor timing of product releases
Project Communication Management | Client Confusion | Communications are very complex and/or detailed
| Client Support | Lack of buy-in for project
| Dissemination | - Number of stakeholders - Reliance on other departments for communication
Procurement Management | Outsourcing Issues | - Outsourcing delays or deliverables not met - Lack of vendor and supply availability